## Slide 1: Interventional Photoacoustic Registration
4/05/11
Robert Kim, BME, AMS
Steven Su, BME, AMS
Saurabh Vyas, BME, EE
Mentors: Dr. Emad Boctor, Dr Russell Taylor

## Slide 2: Outline of Talk
Background
Setup
Milestones
Deliverables
Results
Timeline
Unresolved Dependencies

## Slide 3: Background: Photoacoustic Effect
When matter is exposed to high frequency pulses of light, most of the light’s energy will be absorbed by the molecules in the incident matter.
As the energy from the light is converted to heat, the molecules become thermally excited.
Heat waves will then radiate away from the matter causing sound waves due to pressure variations in the environment around the medium.
These sound waves can then be detected by acoustic devices such as ultrasound (US).

## Slide 4: Current Setup
Sonix CEP
Ultrasound system
SonixDAQ
Module
MATLAB
Software
DAQControl
Software
SonixRP
Software
L14-5W
Transducer
Phantom
Surelite II
Laser system

## Slide 5: Milestones
Old
New
Milestone 1:
  Calibrate and Synchronize Laser with US.
  Build Phantoms.
  Completion Date: 3/11
Milestone 2:
  532 nm one point experiment.
  Completion Date: 4/12
Milestone 3:
  532 nm three point experiment.
  Completion Date: 5/1
Milestone 4:
  Camera integration.
  Registration between camera and US.
  Completion Date: 5/15
Milestone 1: Unchanged
  Completed 3/11
Milestone 2:
  1064 nm one point experiment.
  1064nm three point experiment.
  Rigid transform from US-Model.
  Completed 3/28
Milestone 3:
  Setup 532 nm laser.
  532 nm one point experiment.
  532nm three point experiment.
  Expected Completion 4/18
Milestone 4:
  Integrate camera.
  Registration between camera and US.
  Expected Completion 4/22
Milestone 5:
  BMEStart competition.
  Expected Completion 5/15
Currently Working On

## Slide 6: Deliverables
Minimum: (Achieved)
  Phantoms
  B-mode images of 1064 nm one point experiment
  B-mode images of 1064 nm three point experiment
  Functioning setup of 532 nm laser source
Expected: (Almost Achieved)
  B-mode images of 532 nm one point experiment
  B-mode images of 532 nm three point experiment
  Demonstration of integrated stereo camera
Maximum:
  Video demonstration of registration of US to camera
  Completed Documentation/Application for BMEStart Competition

## Slide 7: Timeline

## Slide 8: Unresolved Dependencies
Dependency: Laser beam splitters
  Resolution Plan: Dr. Taylor agreed to purchase when needed.
  Resolve By: 4/14
  Resolved: No
  Fallback Plan: See if Dr. Kang has one?
  Affects: Milestone 3 and 4