## Slide 1: Interventional Photoacoustic Registration
4/7/11
Robert Kim, BME, AMS
Steven Su, BME, AMS
Saurabh Vyas, BME, EE
Mentors: Dr. Emad Boctor, Dr Russell Taylor
Special Thanks to: Nathanael Kuo

## Slide 2: Outline of Talk
Background
Setup
Milestones
Deliverables
Timeline
Unresolved Dependencies
Results

## Slide 3: Background: Photoacoustic Effect
When matter is exposed to high frequency pulses of light, most of the light’s energy will be absorbed by the molecules in the incident matter.
As the energy from the light is converted to heat, the molecules become thermally excited.
Heat waves will then radiate away from the matter causing sound waves due to pressure variations in the environment around the medium.
These sound waves can then be detected by acoustic devices such as ultrasound (US).

## Slide 4: Current Setup
Sonix CEP
Ultrasound system
SonixDAQ
Module
MATLAB
Software
DAQControl
Software
SonixRP
Software
L14-5W
Transducer
Phantom
Surelite II
Laser system

## Slide 5: Milestones
Old
New
Milestone 1:
  Calibrate and Synchronize Laser with US.
  Build Phantoms.
  Completion Date: 3/11
Milestone 2:
  532 nm one point experiment.
  Completion Date: 4/12
Milestone 3:
  532 nm three point experiment.
  Completion Date: 5/1
Milestone 4:
  Camera integration.
  Registration between camera and US.
  Completion Date: 5/15
Milestone 1: Unchanged
  Completed 3/11
Milestone 2:
  1064 nm one seed experiment.
  1064nm three seed experiment.
  Rigid transform from US-Model.
  Completed 3/28
Milestone 3:
  Setup 532 nm laser.
  532 nm one point experiment.
  532nm three point experiment.
  Expected Completion 4/18
Milestone 4:
  Integrate camera.
  Registration between camera and US.
  Expected Completion 4/22
Milestone 5:
  BMEStart competition.
  Expected Completion 5/15
Currently Working On

## Slide 6: Deliverables
Minimum: (Achieved)
  Phantoms
  B-mode images of 1064 nm one seed experiment
  B-mode images of 1064 nm three seed experiment
  Functioning setup of 532 nm laser source
Expected: (Almost Achieved)
  B-mode images of 532 nm one point experiment
  B-mode images of 532 nm three point experiment
  Demonstration of integrated stereo camera
Maximum:
  Video demonstration of registration of US to camera
  Completed Documentation/Application for BMEStart Competition

## Slide 7: Timeline

## Slide 8: Unresolved Dependencies
Dependency: Laser beam splitters
  Resolution Plan: Dr. Taylor agreed to purchase when needed.
  Resolve By: 4/14
  Resolved: No
  Fallback Plan: See if Dr. Kang has one?
  Affects: Milestone 3 and 4

## Slide 9: 1064 nm One Seed

## Slide 10: 1064 nm Three Seeds

## Slide 11: 532 nm No Seeds (No Lens or Fiber)

## Slide 12: 532 nm No Seeds (Lens Only)

## Slide 13: 532 nm No Seeds (With Lens and Fiber)

## Slide 14: 1064 nm No Seeds (With Lens and Fiber)
Fiber melted due to high energy of laser.
With beam splitter, energy is split as well
  Melting may not be an issue once the splitter is obtained
  The beam splitter is also required to complete Milestone 3 and Milestone 4.

## Slide 15: 1064 nm No Seeds (With Lens)

## Slide 16: Future Work
Figure out how to increase the power of the 532 nm laser
  Proper Mirror Alignment within the laser source
  Q-Switching?
Obtain/order beam splitter needed to do three point experiment.
  This can be done regardless of whether 532 nm works or not
Integrate the camera to perform registration
Finish BMEStart Competition portfolio (By: 5/15)

## Slide 17: Milestones
Milestone 1: Unchanged
  Completed 3/11
Milestone 2:
  1064 nm one seed experiment.
  1064nm three seed experiment.
  Rigid transform from US-Model.
  Completed 3/28
Milestone 3:
  Setup 532 nm laser.
  532 nm one point experiment.
  532 nm three point experiment.
  Expected Completion 4/18
Milestone 4:
  Integrate camera.
  Registration between camera and US.
  Expected Completion 4/22
Milestone 5:
  BMEStart competition.
  Expected Completion 5/15
Old
New
Milestone 1:
  Calibrate and Synchronize Laser with US.
  Build Phantoms.
  Completion Date: 3/11
Milestone 2:
  532 nm one point experiment.
  Completion Date: 4/12
Milestone 3:
  532 nm three point experiment.
  Completion Date: 5/1
Milestone 4:
  Camera integration.
  Registration between camera and US.
  Completion Date: 5/15
Currently Working On
Resolve by: 4/14