## Slide 1: Force Controlled Elastography with DaVinci Toolkit
Xingtong Liu
Preetham, Dr. Boctor, Dr. Taylor
Notes: I’ve asked my team to come up with a few updates in various areas for this presentation. Rather than standing in the front of the room talking at you, we wanted to use this time as more of an open forum from our seats.
I have 3 slides that I want to go over quickly.

## Slide 2: Background
Motivation
Palpation is generally limited to superficial structures and stiffer masses located deep in the body almost certainly cannot be detected by surface palpation.
Elastography imaging can provide tissue stiffness as an additional and clinically relevant information, which can be very helpful in distinguishing among different tissues for tumor recognition and intraoperative registration etc.
Ultrasound Elastography integrated into the DaVinci Research Toolkit (DVRK) robot system can allow for further research based on that.
Goal
Integrate ultrasound probe and software into the DVRK robot system.
Use DVRK robot system to generate ultrasound elastography image and locate stiff features in a phantom based on that.

## Slide 3: Proposed Plan
  Milestone
Flowchart

## Slide 4: Technical Overview
Ultrasound Probe Calibration
If scale is unknown,
If scale is known,
Hsu, P., Prager, R. W., Hsu, P., Prager, R. W., Gee, A. H., & Treece, G. M. (2007). Freehand 3-D Ultrasound Calibration: A Review. Engineering, (December).

## Slide 5: Technical Overview
Hybrid force feedback control
Primitive I. Primitive II.
where is a constant incremental step along the surface of the model and is the incremental velocity calculated based on contact force and some desired bias force . is a projection matrix decomposing the forces in the normal direction of the surface.
Chalasani, P., Wang, L., Roy, R., Simaan, N., Taylor, R. H., & Kobilarov, M. (n.d.). Concurrent Nonparametric Estimation of Organ Geometry and Tissue Stiffness Using Continuous Adaptive Palpation.

## Slide 6: Technical Overview
Ultrasound Elastography
Elastography imaging techniques are based on the hypothesis that soft tissues deform more than stiffer tissue, and these differences can be quantified in images of the tissue strain tensor or the Young’s modulus
2-D displacement estimation using dynamic programming
Where,
Rivaz, H., Boctor, E., Foroughi, P., Zellars, R., Fichtinger, G., & Hager, G. (2008). Ultrasound elastography: A dynamic programming approach. IEEE Transactions on Medical Imaging, 27(10), 1373–1377.

## Slide 7: Deliverables
  Minimum deliverable
  DaVinci ultrasound tool and ultrasound system integration into DVRK system
  Expected deliverable
  Ultrasound imaging with force feedback control
  Maximum deliverable
  Ultrasound elastography with DVRK

## Slide 8: Dependencies
Dependency | Status | Fallback
Collaboration |  | 
Ultrasound probe kinematics calibration with Preetham | Solved | 
Ultrasound probe scan plane calibration with Alexis | Solved | 
Hardware |  | 
DVRK hardware | Solved | 
Compatible ultrasound probe | Solved | 
Ultrasound machine | Solved | 
Elasticity ultrasound phantom with stiff features and proper weight from MUSIIC group | Pending | Build a proper one with gel by myself
Software |  | 
DVRK software | Solved | 
Ultrasound data acquisition API | Solved | 
Robot operating system (ROS) | Solved | 
Proper visualization library | Solved | 
Elastography code from MUSIIC group | Pending | Implement one by myself

## Slide 9: Timeline
Task Name | Start Date | End Date | Duration | Status
Milestone 1 - Ultrasound data acquisition integration | 02/28/17 | 03/14/17 | 11d | In Progress
Learn DVRK software framework | 02/28/17 | 03/06/17 | 5d | In Progress
Learn ultrasound data acquisition API | 03/07/17 | 03/08/17 | 2d | Not Started
Integrate API into DVRK framework | 03/09/17 | 03/10/17 | 2d | Not Started
Ultrasound image display in DVRK framework | 03/13/17 | 03/14/17 | 2d | Not Started
Milestone 2 - Ultrasound probe calibration | 03/15/17 | 03/28/17 | 10d | Not Started
Ultrasound probe install | 03/15/17 | 03/15/17 | 1d | Not Started
Ultrasound kinematics calibration | 03/16/17 | 03/20/17 | 3d | Not Started
Ultrasound scan plane calibration | 03/21/17 | 03/24/17 | 4d | Not Started
Calibration results verification | 03/27/17 | 03/28/17 | 2d | Not Started
Milestone 3 - Hybrid force feedback control with ultrasound probe | 03/29/17 | 04/07/17 | 8d | Not Started
Learn force sensor data acquisition API and force control in DVRK | 03/29/17 | 03/30/17 | 2d | Not Started
Get a ready-to-use elasticity phantom or make a proper one | 03/31/17 | 04/03/17 | 2d | Not Started
Install force sensor underneath phantom and test force sensor data acquisition | 04/04/17 | 04/04/17 | 1d | Not Started
Move ultrasound probe on phantom surface with constant force | 04/05/17 | 04/07/17 | 3d | Not Started
Milestone 4 - Ultrasound Elastography integration | 04/10/17 | 04/25/17 | 12d | Not Started
Obtain Ultrasound Elastography source code or implement one | 04/10/17 | 04/14/17 | 5d | Not Started
Integrate Ultrasound Elastography into DVRK software framework | 04/17/17 | 04/20/17 | 4d | Not Started
Test Ultrasound Elastography on phantom | 04/21/17 | 04/25/17 | 3d | Not Started
Project refinement and further verification | 04/26/17 | 05/12/17 | 13d | Not Started
Seminar presentation | 03/06/17 | 03/08/17 | 3d | Not Started
Checkpoint presentation | 04/03/17 | 04/05/17 | 3d | Not Started
Final presentation | 05/13/17 | 05/17/17 | 4d | Not Started

## Slide 10: Management
Weekly meeting with Dr. Taylor on Model and Registration Meeting.
Weekly meeting with Preetham on pre-scheduled time.
Regular meeting with Dr. Boctor.

## Slide 11: Reading List
[1] Chalasani, P., Wang, L., Roy, R., Simaan, N., Taylor, R. H., & Kobilarov, M. (n.d.). Concurrent Nonparametric Estimation of Organ Geometry and Tissue Stiffness Using Continuous Adaptive Palpation.
[2] Gennisson, J. L., Deffieux, T., Fink, M., & Tanter, M. (2013). Ultrasound elastography: Principles and techniques. Diagnostic and Interventional Imaging, 94(5), 487–495.
[3] Hsu, P., Prager, R. W., Hsu, P., Prager, R. W., Gee, A. H., & Treece, G. M. (2007). Freehand 3-D Ultrasound Calibration: A Review. Engineering, (December).
[4] Jeong, W. K., Lim, H. K., Lee, H.-K., Jo, J. M., & Kim, Y. (2014). Principles and clinical application of ultrasound elastography for diffuse liver disease. Ultrasonography (Seoul, Korea), 33(3), 149–60.
[5] Krupa, A. (2006). Automatic calibration of a robotized 3D ultrasound imaging system by visual servoing. Proceedings - IEEE International Conference on Robotics and Automation, 2006(May), 4136–4141.
[6] Krupa, A., & Chaumette, F. (2005). Control of an ultrasound probe by adaptive visual servoing. 2005 IEEE/RSJ International Conference on Intelligent Robots and Systems, IROS, 2007–2012.
[7] Manuscript, A., & Elastography, Q. U. (2010). NIH Public Access, 4(3), 323–338.
[8] Rivaz, H., Boctor, E., Foroughi, P., Zellars, R., Fichtinger, G., & Hager, G. (2008). Ultrasound elastography: A dynamic programming approach. IEEE Transactions on Medical Imaging, 27(10), 1373–1377.
[9] Chalasani, P., Wilkening, P., Chen, Z., & Taylor, R. (2014). CSA NRI Research Environment.
[10] Mueller, K. (1990). Introduction to Medical Imaging Ultrasound Imaging Milestone applications : Non-linearity.