## Sheet1
Dependency | Need | Status | Followup | Contingency Plan | Planned | Hard DDL
Oscillscope | In replace for ventilator in training CV model | Bought | N/A | N/A | 2021-02-26 | 2021-02-28
Tensorflow/OpenCV | Training model | Installing | N/A | N/A | 2021-02-27 | 2021-03-01
Camera | Taking real time input | Ordering | N/A | Take videos and pictures via personal iphone | 2021-03-03 | 2021-03-05
X-code | Building user interface | Installed | N/A | N/A | 2021-02-26 | 2021-02-26
Building blocks (T-slot), axels, screws etc | To build cartesian robot | Ordering | N/A | Buy Prebuilt Cartesian Robot | 2021-03-05 | 2021-03-07
Motors (stepper motor, servo etc) | to actuate the end effector | Ordering | N/A | Buy Prebuilt Servo Assembly | 2021-03-05 | 2021-03-07
Basic tools | to assemble and manipulate material | Ordering | N/A | N/A | 2021-03-01 | 2021-03-05
3D prototypes printing (outsourced) | to prototype end effector | Selecting Manufacture | 2021-03-01 | Physically pick up the prototype | 2021-03-05 | 2021-03-09
Measuring equipments | To quantify testing result | ordering | 2021-03-10 | Borrow Equipment from my Lab in China | 2021-03-15 | 2021-03-17