## Slide 1: Mixed Reality Surgical Team Training
Team member: Haochen Wei
Mentors: Peter Kazanzides; Dayeon Kim
Feb 24th 2022

## Slide 2: Background
Endoscopic surgery is important in modern medicine.
Lots of good things: minimally invasive, small blood loss, recover quickly, etc.
Drawback: Endoscopic surgery is difficult to train due to the limitation of patient resources, and safety issues.
Nobody wants to be a teaching aid of a surgery.
Current solution: Animal Model (Pig)

## Slide 3: Goal
We might solve the issue by implementing mixed reality surgical training.
Mixed reality is not a new technology and has been explored for long time
There are several dedicated mixed reality training tools that are used to training a specific surgery.
We want to create a more general mixed reality environment.
No limitation on tool numbers
No limitation on tool shapes
Can be combined with Da Vinci Robot

## Slide 4: Surgical Team Training Concept
Simulator
Point clouds of hand-held (and robotic) instruments from sensorized phantom
3D endoscope video (simulated patient, real instruments)
HMD optional (could deliver training info)
Anatomy is simulated, instruments are real.
Realistic physical interaction with system (except for direct interaction with anatomy)
2D video
Endoscope video (of instruments)
Sensorized phantom
robot motion
Sensorized phantom provides 3D point clouds of inserted instruments
Unmodified da Vinci data
Simulator video output
Sensorized phantom output

## Slide 5: Surgical Team Training Minimal Deliverable
Simulator
Point clouds of hand-held (and robotic) instruments from sensorized phantom
2D endoscope video (Point Cloud)
Endoscope video (of instruments)
Sensorized phantom
Unmodified da Vinci data
Simulator video output
Sensorized phantom output
Point clouds of hand-held (and robotic) instruments from sensorized phantom
2D video from the perspective of the endoscope output to the standalone monitor.
Notes: PK: Hopefully, you will be able to do more than this, since this result would look worse than just showing the real endoscope video

## Slide 6: Surgical Team Training Expected Deliverable
Simulator
Point clouds of hand-held (and robotic) instruments from sensorized phantom
2D video (Point Cloud and simulated patient)
Endoscope video (of instruments)
Sensorized phantom
Unmodified da Vinci data
Simulator video output
Sensorized phantom output
Minimal Deliverable+
Overlay the patient’s 3D model with the obtained point cloud. (Proof of concept)
Collision detection between the tools and virtual organ model.

## Slide 7: Technical Approach
Point clouds of hand-held (and robotic) instruments from sensorized phantom
Passive method: Using 4 cameras fixed at corners of the phantom, 2 for each side. Then using the conventional triangulation method to obtain the point cloud.
P: Cheap; High Accuracy;
C: Might encounter problems for thin tools.
Active method: Using 2 Time of Flight RGBD cameras to obtain the point cloud, 1for each side.
P: Easy for obtaining point clouds
C: Low accuracy on close range; Relatively expensive
The current plan is pursuing both ways in parallel and deciding which is better. Then carry on with the one with the better results.
Notes: PK: Not sure what you mean by “Initiative method”

## Slide 8: Technical Approach
2D video from the perspective of the endoscope output to the stand-alone monitor
If endoscope fixed on the da Vinci Robot:
Forward Kinematics provided from robot. Registration between robot and phantom is needed. Render the point cloud accordingly.
If endoscope is hand-held:
AR-tag attached on the endoscope to localize the position and pose of endoscope. Render the point cloud accordingly.
Notes: PK: If endoscope attached to robot, why do you need AR tag? And, where do you plan to attach this tag, on the inside of the phantom? With the robot, you just need to do a one-time registration between the robot and the phantom. For a hand-held endoscope, this is more difficult and one possible solution is to attach a tag, as you mention.

## Slide 9: Technical Approach
Overlay the patient’s 3D model with the obtained point cloud. (Proof of concept)
Place some virtual cube/cylinders within the virtual space inside the phantom. Overlay the point cloud on it.
Collision detection between the tools and virtual organ model.
Detect how many points are located within the virtual cube/cylinders. If the number of points exceeds a certain threshold, then report the collision.
A possible challenge is the quality of the point cloud.

## Slide 10: Timeline
Chart: Project timeline
| Designing mount bracket | Installision | Point clouds using RGB Camera | Point clouds using ToF Camera | Deciding which method | Rendering the point cloud asynchronous | Improving the point cloud quality | Researching on Real-time rendering | Locolization of endoscope | Achieve real time rendering | Overlay 3d model to rendered graph | Exploring point collision within the data | Implementing the Collision detection | Wrap-up the research | Final report
Start date | 44613 | 44613 | 44624 | 44624 | 44624 | 44624 | 44624 | 44638 | 44638 | 44645 | 44659 | 44666 | 44673 | 44680 | 44680
Range | 11 | 11 | 7 | 7 | 14 | 14 | 21 | 7 | 14 | 14 | 14 | 7 | 7 | 7 | 7
Notes: PK: This seems overly optimistic

## Slide 11: Milestone
Date | Object | Explain
3/4 | Mounting the cameras and calibrating them. | Fixing all hardware, freezing the hardware stuff.
3/25 | Finishing improving the point cloud data. | The project is aiming to achieve real-time rendering. The algorism of collecting real-time point cloud and filtering out noise should be given by now.
4/8 | Finish minimal object | The real-time rendering object should be achieved.
4/28 | Finish the expected object | Collision detection achieved
Notes: PK: This seems overly optimistic

## Slide 12: Dependency and Management
Items | Sources | Date | Status | Priority and Possible effect
5 x RGB Cameras | Purchase | 3 /4 | Searching | 1. Cannot perform research without it.
2 x ToF RGBD Cameras | Purchase | 3 /4 | Searching | 2. Still can perform experiment without it but will not be able to perform comparison
Mounting Bracket for Cameras | 3D printing | 3 /4 | Drawing CAD now | 2. Have alternative method but will significantly influence accuracy of cameras.
DVRK | LCSR Lab | 3/18 | Approved by Professor Peter | 2. Can perform the experiment without it. Only be able to use AR-tag to localization the endoscope.
Abdominal Phantom | LCSR Lab | 3 /4 | Approved by Professor Peter | 3. Can perform the experiment without it. Easily find alternatives e.g cardboard box.
Computer | Myself | Now | Available | 1. Cannot perform research without it.
Endoscopic tools | LCSR Lab | 3 /4 | Approved by Professor Peter | 3. Can perform the experiment without it. Easily find alternatives e.g pen
Rendering Software (UE5/Unity) | Online | 3 /4 | Available online at no cost | 1. Cannot perform research without it.
Mentor: Professor Peter Kazanzides; Dayeon Kim
Meeting: Friday 3PM-4PM every week
Notes: PK: You could still perform research without the ToF cameras. I changed “Phantom” to “Abdominal Phantom” because that is what I think you mean.

## Slide 13: Reference and Reading list
Qian L., Zhang X., Deguet A., Kazanzides P. (2019) ARAMIS: Augmented Reality Assistance for Minimally Invasive Surgery Using a Head-Mounted Display. In: Shen D. et al. (eds) Medical Image Computing and Computer Assisted Intervention – MICCAI 2019.
Azimi, Ehsan et al. “An Interactive Mixed Reality Platform for Bedside Surgical Procedures.” MICCAI (2020).
Zollhöfer, Michael & Stotko, Patrick & Görlitz, Andreas & Theobalt, Christian & Nießner, Matthias & Klein, Reinhard & Kolb, Andreas. (2018). State of the Art on 3D Reconstruction with RGB‐D Cameras. Computer Graphics Forum. 37. 625-652. 10.1111/cgf.13386.
Han, X., Laga, H. Bennamoun, M. Image-Based 3D Object Reconstruction: State-of-the-Art and Trends in the Deep Learning Era. IEEE Transactions On Pattern Analysis And Machine Intelligence. 1578-1604 (2021,5), http://dx.doi.org/10.1109/TPAMI.2019.2954885

## Slide 14: Thank you Questions?