## Sheet1
| Activities | Result | Deliverables | Due | Status
Minimum | AMBF simulation of REMS Galen robot | Environment for rapid virtual prototyping of controller available | AMBF Simulation setup, Virtual machine state, record environment variables | 2023-02-27 | Done
| Frequency domain admittance controller | Controller Prototype ready for reviewing transparency style optimization | Place controller framework in repository, figures showing simulation for time, force, performance, stability | 2023-03-13 | Done
| Transparency Optimization | Controller Prototype for moving to low level controller | Add updates to repository, figures comparing transparency optimal control to basic frequency admittance control | 2023-03-22 | Done
Expected | Mid level Galen controller implimentation | Experimentation and debugging results of simulation controller compared to updated controller for real world | Add updates to repository, record performance from different controllers for the Galen robot including figures, controller ready for demos and presentation | 2023-04-25 | In Progress
| System Identification In AMBF and on the Real robot | Transfer functions for the robo t to be used in the AMBF simulation and on the real robot | A set of transfer functions coupled with stability maps and cost maps that allow for optimal choice of Admitance mass and damping | 2023-04-03 | In Progress
| Design objective specified metrics for critiquing transparency | Measurable standards that will be used to test the different controllers for the Galen robot | Documentation of the desired standards for transparency, clear performance characteristics, and ways to evaluate the truly optimal controller from an analytic perspective | 2023-04-11 | Done
| Evaluate controller transparency | Real world data of controller comparisons for optimal transparency | Objective analytical data for different frequency controllers or other Galen controllers that can be compared with performance and user preference to select the best controller | 2023-04-18 | In Progress for real robot
Updated Maximum | Implement Virtual Fixtures on Real Galen hardware | Use AMBF vitual collisions or use python simulated contact to manage reversing the force or velocity of the current trajectory to create a virtual fixture | A virtual fixture implementation that can be hard coded and integrated with specific surgical applications | 2023-05-05 | Waiting
Extended Maximum | Design User study plan for testing controllers | Answer what level of testing is needed, how many users, how to randomize the tests | Test setup ready for users preference with controllers with a clear survey that allows user to report preference in a measurable way, documentation fully caught up | 2023-04-18 | ON HOLD
| Recruit users and analyze user study data | Fliers, email, subjects with contact info aware of times and locations to assist in user study | Report and analyze available data to determine the most preferable controller, prepare for presentation/papers | 2023-05-18 | ON HOLD