## Sheet1
Dependency | Need | Contingency Plan | Planned Deadline | Hard Deadline | Status
Access to Computer | Need a computer with a Linux platform | Use a lab computer | 2023-02-08 | 2023-02-13 | Completed
Access to Galen AMBF Model | File access and editing permissions | Create a basic 3D model and crude dynamics | 2023-02-14 | 2023-02-20 | Completed
Software Installation MATLAB SIMULINK | License | Use Lab Computer with preinstalled software | 2023-02-08 | 2023-02-13 | Completed
Software Blender and AMBF Addon | Installation Instructions | Use Lab Computer with preinstalled software | 2023-02-08 | 2023-02-13 | Completed
Galen Robot and Controller Access | Anton and Adnon complete controller pipeline for galen task space and joint space control | Go without Galen hardware implementation. Implement on similar robot or move on without implementation | 2023-03-15 | 2023-04-15 | Completed
IRB for user study | IRB Approval | Go without the User Study | (Submission 20-Feb) 4-May | (Submission 24-Feb) 14-May | On Hold
Formulas:
Hard Deadline = [Planned Deadline]+5