## Slide 1: Creation of a Novel Real-time Communication Solution for Sepsis Management
Group 23
Students: Sofia Posada, Rahul Swaminathan Mentors: Dr. Jim Fackler, Dr. Kimia Ghobadi

## Slide 2: Project Summary
Goal: Create a platform for sepsis management to allow antibiotics to be delivered from the pharmacy to the patient in under one hour
Solution:
  Track antibiotics
  Visualize process map
  Alert relevant sepsis team members
Notes: Reduce mortality rates and decrease length of stay in hospital

## Slide 3: Project Status
Minimum Deliverable | Associated Tasks/Milestones | Expected Date | Status
Finalized process map of sepsis management workflow (Sofia and Rahul) | Shadow Dr. Fackler in the PICU to observe the steps of antibiotic delivery during sepsis management | 2/21 | Completed 2/21
 | Identify all team members involved in sepsis management at a role-level | 3/2 | Completed 3/2
 | Conduct clinician/provider interviews to augment the existing process map and identify commonly used communication platforms | 3/7 | Completed 3/9
Complete dataset of timestamps and locations for antibiotic delivery | Place a locator tag inside the bag containing the antibiotics to track its location and time throughout the delivery process and fill in the gaps in the existing timestamp data (Sofia) | 3/9 | Infeasible for now
Short report of gap analysis showing where a communication solution is most needed | Analyze the complete partial timestamp data and see where the antibiotics are held up for the longest periods of time in order to cross-reference that with the process map to see where a solution would be most useful (Sofia and Rahul) | 3/16 4/10 | Delayed due to IRB and change in data management staff

## Slide 4: Project Status (continued)
Expected Deliverable | Associated Tasks/Milestones | Expected Date | Status
Physical prototype of communication solution that allows providers to visualize where the antibiotics are within the hospital | Test out the Versus Information System (VIS) to see if antibiotic location can be accurately and reliably tracked and exported outside of their software. Use barcode scanning as a tracking alternative if this doesn't work. (Sofia) | 4/6 4/14 | Delayed – preemptively extended the deadline
 | Correlate antibiotic location with the roles of team members as described in the process map (Sofia) | 4/20 | On track
 | Set up alerts to automatically inform the relevant personnel when it is their turn (Rahul) | 4/27 | On track

## Slide 5: Project Status (continued)
Maximum Deliverable | Associated Tasks/Milestones | Expected Date | Status
Implemented prototype of communication solution that uses a monitor to display the location of the antibiotics and whose turn it is within the process map | Set up an additional monitor in the PICU’s huddle room that displays the location of the antibiotics as well as the process map (Rahul) | 5/4 | Not started
 | Program the process map to light up in the relevant sections when the antibiotics have reached that part of the workflow (Rahul) | 5/11 | On track
Dataset of timestamps and locations for antibiotic delivery after the solution is implemented | As done earlier, place a locator tag inside the bag containing the antibiotics to track its location and time throughout the delivery process in order to see how the efficiency of antibiotic delivery has changed as a result of the implemented solution (Sofia) | 5/18 | Infeasible due to time restrictions

## Slide 6: Timeline

## Slide 7: Current Work – Process Map
PICU Doctor
Pharmacy
PICU Nurse

## Slide 8: Current Work – Tracking Documentation
Original plan - Versus Information System (VIS) - not feasible
“Implementation of a Web-based medication tracking system in a large academic medical center” (Calabrese and Williams, 2012)
Requirements (End-user needs):
  Antibiotic location should be accurately and reliably tracked.
  Allow sepsis team members to quickly identify the location of a specific antibiotic in case of an emergency.
  The system should provide a record of all interactions with the antibiotic to enable efficient tracking and monitoring.
System Design:
Inputs:
  Barcode scanner
  Database for storing data
  Label printer for creating barcode stickers (pharmacy has this)
System:
When an antibiotic is passed in the pharmacy, a unique barcode sticker is generated and attached to the outside of the antibiotic packaging.
When a sepsis team member receives the antibiotic, they scan the barcode with a scanner app to record the timestamp and location associated with the interaction.
The system stores this data in a database for future reference.
When the antibiotic is moved to a new location or handed over to another team member, the process repeats
Outputs:
  Location data for each interaction with the antibiotic
  Timestamp data for each interaction with the antibiotic

## Slide 9: Current Work – Design Documentation
Requirements (End-user needs):
  Sepsis team members must be able to view the real-time location of the antibiotics within the PICU
  Sepsis team members must be able to see how the antibiotic delivery is progressing within the process map
  Sepsis team members must be notified once the antibiotics have reached predetermined locations
System Design:
Inputs:
  Real-time location of antibiotics
  Process map of sepsis management workflow
  Real-time location of sepsis team members (ideal but not necessary)
System:
  Relational database of antibiotic locations, relevant sepsis team members, and steps in the process map
  EPIC Secure Chat - group chat with all sepsis team members
Outputs:
  Dynamic process map showing current and next steps depending on the location of the antibiotics
  Notification system to alert sepsis team members at each stage of the antibiotic delivery

## Slide 10: Dependencies
Dependency | Need | Status | Planned Deadline | Hard Deadline | Contingency Plan
IRB approval for tracking | Tracking location of antibiotics from the pharmacy | No approval needed for sticking a gps tag in the antibiotics bag because someone from the pharmacy is on the existing IRB | 2/16 | 2/28 | N/A
Access to Versus Information System technology | Tracking location of antibiotics from the pharmacy | Still need access to the API Cannot get ahold of the tags | 2/28 | 3/16 | Use our own tracking device like an Apple AirTag and find out how to export that location data Use barcode system
Access to timestamp data | Gap analysis for identifying solution space | We have some of the data but not all. IRB change was approved! | 2/20 | 3/16 4/10 | Conduct gap analysis using limited available data in combination with nurse interviews
HIPAA Training | Access to certain datasets and Epic Secure Chat | All trainings are complete | 2/28 | 4/13 | May be able to use anonymized data for all analysis purposes
Notes: Meeting tomorrow
VIS more useful less manual more automatic
Dave (pharmacist but also in charge of VIS tags) in surgery

## Slide 11: Copyright The Johns Hopkins University 2022. All rights reserved.